## Roadmap
VOICE HUB — DELIVERY ROADMAP
Sequence-based production plan • Version 1.0 • 2026-08-15 • Calendar commitments intentionally TBD
TOTAL STORIES |  | 38 |  | P0 REMAINING |  | 24
DONE |  | 12 |  | BLOCKED |  | 3
Milestone | Outcome | Stories | Done | In progress | Blocked | Progress | Exit gate
M0 — Product Baseline & Architecture | A separate Voice Hub product with explicit domains, provider contracts, and a production delivery baseline. | 6 | 5 | 1 | 0 | 83.33% | Repository boundaries, product policy, API/domain contracts, and test baseline are approved.
M1 — Core Voice Note Creation | A signed-in user can create, preview, save, translate, and share a Nigerian-language voice note. | 9 | 1 | 3 | 0 | 11.11% | Five-language create flow passes device/provider, audio, offline, failure, and WhatsApp share acceptance tests.
M2 — Editorial Voice Channels | People can follow reviewed gist, relationship, and jobs channels and opt in separately to WhatsApp delivery. | 6 | 3 | 1 | 1 | 50% | Editorial provenance, subscription consent, delivery reconciliation, opt-out, and takedown operations are production-ready.
M3 — Private AI Companions | Adults can use clearly disclosed fictional companions in private conversations with strong safety and data controls. | 5 | 3 | 0 | 1 | 60% | Age/disclosure gates, semantic safety, private authorization, block/report, export, and deletion pass adversarial testing.
M4 — Cloud Production & Trust | The service runs reliably and affordably on Cloudflare-compatible infrastructure with production identity and operations. | 6 | 0 | 1 | 1 | 0% | Production auth, storage, queues, observability, security review, backups, and cost alarms are verified under load.
M5 — Beta, Launch & Growth | A measurable closed beta graduates through documented quality, store, support, and product-health gates. | 6 | 0 | 0 | 0 | 0% | Language quality, crash-free use, latency, safety, consent, support, and Play release thresholds are met.
Interpretation: progress counts Done stories only. Blocked items are external or unselected decisions, not hidden engineering estimates.

## Epics
VOICE HUB — EPICS
Objectives and formula-driven story completion by epic
Epic ID | Milestone | Epic | Owner | Objective | Stories | Done | Progress
E01 | M0 | Product boundaries and catalog | Product | Define launch domains, language catalog, voice provenance, and excluded uses. | 3 | 2 | 66.67%
E02 | M0 | Core service contracts | Backend | Establish provider, media, publishing, delivery, and companion boundaries with deterministic tests. | 3 | 3 | 100%
E03 | M1 | Voice authoring and language | Android | Deliver a five-language create flow with explicit device and Voice Hub voice modes. | 4 | 0 | 0%
E04 | M1 | Audio lifecycle and sharing | Android + Backend | Produce valid Ogg/Opus, preview it, save it, and share it safely. | 5 | 1 | 20%
E05 | M2 | Editorial publishing and feed | Editorial Ops + Backend | Publish reviewed, attributable channel episodes and deliver a useful in-app feed. | 3 | 1 | 33.33%
E06 | M2 | WhatsApp subscriptions and delivery | Backend + Operations | Collect explicit consent and deliver/reconcile compliant WhatsApp messages. | 3 | 2 | 66.67%
E07 | M3 | Companion conversations | Android + Backend | Provide private fictional companion chat and voice responses without mixing it with broadcast channels. | 2 | 1 | 50%
E08 | M3 | Companion trust and privacy | Trust & Safety | Enforce disclosure, adult gates, anti-dependency policy, user control, and incident response. | 3 | 2 | 66.67%
E09 | M4 | Identity, authorization, and data protection | Platform | Authenticate users and protect private, publisher, and operational data end to end. | 3 | 0 | 0%
E10 | M4 | Cloud operations and cost | Platform | Operate workers, data, media, observability, and cost controls on a production cloud path. | 3 | 0 | 0%
E11 | M5 | Quality and release readiness | QA + Product | Prove language, reliability, safety, and Android release quality before expansion. | 3 | 0 | 0%
E12 | M5 | Measurement and controlled growth | Product + Data | Measure activation and retention while preserving privacy and controlling rollout. | 3 | 0 | 0%

## User Stories
VOICE HUB — USER STORIES
Editable delivery backlog • Status, priority, dependencies, acceptance criteria, release gates, and evidence
Definition of Done: acceptance criteria pass; required tests and operational evidence are linked; privacy/safety controls are verified; release gate has no unresolved blocker.
Story ID | Milestone | Epic | Domain | Persona | User story | Acceptance criteria | Priority | Status | Dependencies | Release gate | Evidence / notes
VH-001 | M0 | E01 | Product | Product owner | As the product owner, I want Create, Channels, and Companions defined as separate domains so that their privacy and delivery rules cannot be confused. | The PRD and architecture name all three domains; companion conversations are never represented as subscriptions; channel fan-out never reads companion threads. | P0 | Done | None | Architecture approval | Documented in current production architecture.
VH-002 | M0 | E01 | Voice Catalog | Listener | As a listener, I want only original, system, or contractually approved voices so that the product does not imply celebrity endorsement. | No UI or API copy says licensed celebrity/public-figure voice; launch catalog records provider, language, consent/provenance class, and active state; celebrity cloning is absent. | P0 | Done | None | Voice provenance review | Visible licensed/public-figure surface removed; provider catalog is original voices only.
VH-003 | M0 | E01 | Language Catalog | Nigerian-language user | As a Nigerian-language user, I want English, Naija Pidgin, Yorùbá, Hausa, and Igbo shown as distinct choices so that I can select the language I intend. | Catalog contains en-NG, pcm-NG, yo-NG, ha-NG, and ig-NG; English and Pidgin are separate; unavailable device voices are labelled unavailable rather than silently substituted. | P0 | In Progress | VH-010 | Language catalog review | Four choices exist; separate English remains planned.
VH-004 | M0 | E02 | Backend | Engineer | As an engineer, I want a standalone Voice Hub backend so that Mama-AI experiments can be reused without becoming a runtime dependency. | Voice Hub has its own service, configuration, migrations, tests, and provider adapters; no runtime import or deployment dependency points to Mama-AI. | P0 | Done | None | Repository boundary review | Standalone FastAPI/PostgreSQL backend exists in voice-hub/backend.
VH-005 | M0 | E02 | Voice Providers | Platform engineer | As a platform engineer, I want one synthesis contract across Spitch, Intron, and YarnGPT so that providers can be selected by language and capability. | Provider request/response contract is typed; Spitch accepts direct Ogg/Opus; WAV providers enter the normalization path; invalid media is rejected with structured errors. | P0 | Done | Provider credentials for live verification | Provider contract tests | Adapters and focused provider tests exist.
VH-006 | M0 | E02 | Delivery | Operations engineer | As an operations engineer, I want durable jobs and an outbox so that synthesis and delivery can be retried without duplicates. | Episode and synthesis job commit atomically; leases prevent double work; content-addressed media is immutable; event replay does not duplicate deliveries. | P0 | Done | PostgreSQL | Idempotency and retry tests | Worker, outbox, delivery planner, and tests exist.
VH-007 | M1 | E03 | Android | Creator | As a creator, I want to choose Device voice or Voice Hub voice so that I understand whether generation is local or cloud-based. | The mode selector explains availability, consistency, data use, and connectivity; selection persists; the app never silently changes mode or provider. | P0 | Planned | VH-003, VH-015, VH-025 | Create UX acceptance test | Current app exposes device TTS only.
VH-008 | M1 | E03 | Android | Creator | As a creator, I want the app to detect installed Android TTS support before generation so that failure is actionable. | The app queries the selected engine/locale; missing language data shows an install/settings action; engine errors are visible; no English fallback occurs without consent. | P0 | In Progress | VH-003 | Device compatibility matrix | Missing-language message exists; deterministic capability model remains planned.
VH-009 | M1 | E03 | Backend | Creator | As a creator, I want a consistent Voice Hub voice for each supported language so that the note sounds similar across devices. | Authenticated create request selects an active language-compatible Spitch profile; response is valid Ogg/Opus; provider failure has a stable code and retry guidance; text is not logged. | P0 | Planned | VH-005, VH-025, production Spitch credentials | Hosted create end-to-end test | Spitch adapter exists but personal Create is not wired to it.
VH-010 | M1 | E03 | Language Services | Creator | As a creator, I want to translate English or another supported Nigerian language into Naija Pidgin before synthesis so that I can send a natural Pidgin note. | Translate action previews editable Pidgin text; source language is explicit or detected with confirmation; user can restore original; translation and synthesis are separate actions; target code is pcm. | P0 | Planned | Spitch Translation API credentials | Pidgin translation quality review | Spitch supports pcm translation; no app flow exists yet.
VH-011 | M1 | E04 | Media | Creator | As a creator, I want every cloud-generated note delivered as standards-compliant Ogg/Opus so that WhatsApp and storage handling are predictable. | MIME is audio/ogg; codec validates as Opus; duration, size, checksum, and storage key are recorded; corrupt or mislabeled bytes are rejected. | P0 | Done | VH-005 | Media conformance tests | Direct Spitch Ogg/Opus validation and WAV normalization path exist.
VH-012 | M1 | E04 | Android Media | Creator | As a creator using Device voice, I want the generated audio converted to Ogg/Opus on-device so that I can save and share the same portable format. | Android 10+ uses a verified Opus/Ogg path; Android 8-9 uses the approved bundled native codec or is explicitly unsupported; golden files pass ffprobe and playback tests; native licenses are documented. | P0 | Planned | Codec implementation decision | Android 8-15 media matrix | Current Device voice output is WAV.
VH-013 | M1 | E04 | Android | Creator | As a creator, I want to preview, pause, replay, rename, save, and delete a generated note before sharing so that I remain in control of the file. | Preview uses the exact share file; saved file appears in user-selected storage; deletion removes app-owned copies; failures preserve the draft; accessibility labels cover playback controls. | P0 | In Progress | VH-011 or VH-012 | Create lifecycle instrumentation | Preview/share exists; save/delete lifecycle is incomplete.
VH-014 | M1 | E04 | Sharing | Creator | As a creator, I want one-tap WhatsApp sharing plus a standard share sheet so that I can send the note where I choose. | WhatsApp target is offered when installed; generic chooser always remains available; content URI is temporary and scoped; AI-audio disclosure accompanies the share; cancellation is non-error. | P0 | In Progress | VH-013 | Physical-device share test | Android share intent exists; disclosure and full compatibility matrix remain open.
VH-015 | M1 | E04 | Backend | Creator | As a creator, I want cloud generation to complete asynchronously so that long provider calls do not hold an API request open. | POST returns a job identifier; status polling or push reports queued/processing/ready/failed; retry is idempotent; completed media URL is time-limited or access-controlled. | P0 | Planned | VH-006, VH-025, VH-029 | Load and retry test | Channel job path exists; personal create contract remains planned.
VH-016 | M2 | E05 | Editorial Ops | Publisher | As a publisher, I want to submit a script with source, review reference, language, and voice profile so that every episode has accountable provenance. | Publish rejects missing source/review; authenticated publisher owns the channel; idempotency key produces one episode; episode and synthesis job commit together. | P0 | Done | VH-005, VH-006 | Publisher authorization test | Publishing service and API tests exist.
VH-017 | M2 | E05 | Editorial Ops | Editor | As an editor, I want distinct policies for gist, relationships, and jobs so that risky or stale content is caught before release. | Gist requires attributable sources and takedown route; relationship content includes advice boundaries; jobs require verified source, expiry, and scam-report path; review checklist is versioned. | P0 | Planned | Named editorial owner | Editorial operating procedure | Seed channel types exist; operational checklist is not implemented.
VH-018 | M2 | E05 | Android | Listener | As a listener, I want to browse, follow, and play the latest channel episodes so that relevant audio is easy to hear. | Catalog groups gist/relationships/jobs; follow state survives restart; feed shows publish time, language, duration, source label, and AI-audio label; playback resumes and handles network loss. | P0 | In Progress | VH-016, VH-025 | Feed and playback test | Live channel catalog and playback components exist; production auth/feed polish remains.
VH-019 | M2 | E06 | Consent | Subscriber | As a subscriber, I want WhatsApp delivery to require separate explicit consent so that following a channel does not enroll my phone number. | Consent stores normalized recipient, version, timestamp, channel/transport scope, and revocation; app follow alone cannot create WhatsApp delivery; consent copy is retrievable for audit. | P0 | Done | VH-025 | Consent audit test | Separate WhatsApp opt-in model and tests exist.
VH-020 | M2 | E06 | WhatsApp | Subscriber | As a subscriber, I want channel audio delivered within WhatsApp policy so that messages arrive without violating the service window. | Inside the customer-service window send audio; outside it send only an approved template/deep link; Meta message ID is stored; retries do not duplicate a delivery. | P0 | Blocked | Verified Meta business, WABA, templates, public webhook | Meta production approval | Dispatcher policy exists; external production approval is missing.
VH-021 | M2 | E06 | WhatsApp | Subscriber | As a subscriber, I want delivery status and STOP/UNSUBSCRIBE handled reliably so that I can see failures and leave immediately. | Webhook signature is verified; sent/delivered/read/failed transitions are idempotent; STOP/UNSUBSCRIBE revokes delivery immediately; retries and invalid signatures are observable. | P0 | Done | Public webhook for live verification | Webhook replay and opt-out test | Signed webhook reconciliation and tests exist.
VH-022 | M3 | E07 | Companions | Adult user | As an adult user, I want to choose a fictional AI girlfriend, AI boyfriend, friend, guy man, or iya agba so that the relationship frame is explicit. | Five profiles are clearly fictional and AI-labelled; romantic profiles are separately tagged; no real-person likeness or implied human operator is used; profile can be changed by starting a new thread. | P0 | Done | None | Companion catalog review | Five companion profiles are seeded in the separate domain.
VH-023 | M3 | E07 | Companions | Companion user | As a companion user, I want private text and voice turns so that the interaction feels natural without becoming a public feed. | Only owner-authorized clients can read/write a thread; input language can be selected; response text is safety-approved before persistence; optional audio uses an approved original voice; failures preserve conversation consistency. | P0 | Planned | Chosen response model, VH-009, VH-025, VH-026 | Companion end-to-end and privacy test | Persistence/API exists; response generation and Android UI do not.
VH-024 | M3 | E08 | Trust & Safety | Romantic companion user | As a romantic companion user, I want explicit AI disclosure and adult age assurance before conversation so that the product sets honest boundaries. | Current disclosure version and age assurance are recorded before thread creation; under-18 or missing assurance is denied; disclosure remains visible in thread; gate changes are audited. | P0 | Done | Production age-assurance policy | Age/disclosure compliance review | Persisted deterministic gate exists; production assurance method remains an open decision.
VH-025 | M4 | E09 | Identity | User | As a user, I want secure sign-in so that my creations, subscriptions, and private conversations are bound to me. | OIDC/Firebase ID token is verified server-side; stable subject is the owner key; expired/invalid tokens fail closed; Android stores tokens in encrypted storage; sign-out clears local secrets. | P0 | Blocked | Firebase project, Android app registration, google-services.json, server audience/issuer | Production identity configuration | Auth seams exist; production Firebase configuration is missing.
VH-026 | M3 | E08 | Trust & Safety | Companion user | As a companion user, I want the AI prohibited from dependency, exclusivity, coercion, or isolation language so that it does not manipulate my relationship with it. | Deterministic rules and a semantic classifier evaluate assistant output before persistence; blocked output is replaced with a safe response; adversarial multilingual tests cover paraphrases; decisions are reviewable without storing unnecessary raw text. | P0 | Blocked | Selected semantic safety model/service and evaluation set | Adversarial companion safety evaluation | Deterministic boundary exists; semantic classifier is not integrated.
VH-027 | M3 | E08 | Privacy | Companion user | As a companion user, I want block, report, export, and delete controls so that I can stop contact and control my data. | Block closes active threads and prevents new turns; report captures category and minimal evidence; export is authenticated JSON; deletion removes thread/message data and scheduled media according to published retention timing. | P0 | Done | Production retention policy | Privacy rights workflow test | Backend operations and tests exist; end-user UI/operations runbook remain planned.
VH-028 | M4 | E09 | Authorization | Security engineer | As a security engineer, I want role and ownership checks at every API boundary so that publishers, users, and operators see only authorized data. | Every private query includes owner subject; publisher mutations require channel ownership/role; admin operations are separately scoped; negative authorization tests cover cross-user and cross-publisher access. | P0 | In Progress | VH-025 | Authorization test suite | Owner/publisher checks exist; production identity mapping remains.
VH-029 | M4 | E09 | Data Protection | Privacy engineer | As a privacy engineer, I want encryption, retention, and redacted telemetry so that sensitive text, phone numbers, and audio are not exposed unnecessarily. | TLS everywhere; secrets are injected; phone numbers encrypted at rest; logs exclude scripts, message bodies, tokens, and raw phone numbers; media/text retention and deletion schedules are documented and enforced. | P0 | Planned | Cloud key management and retention policy | Privacy and security review | Redaction requirements are documented; production enforcement is incomplete.
VH-030 | M4 | E10 | Cloud Platform | Platform engineer | As a platform engineer, I want the backend deployed on Cloudflare-compatible services so that early operating cost remains bounded without sacrificing correctness. | HTTP API, queue workers, database, and object storage have documented Cloudflare mappings; provider calls are asynchronous; migrations are a release step; no FFmpeg dependency is required for Spitch-only launch traffic. | P0 | Planned | Cloudflare account and architecture decision for PostgreSQL-to-D1 compatibility | Cloud staging deployment | Current backend targets FastAPI/PostgreSQL; migration plan is not implemented.
VH-031 | M4 | E10 | Reliability | On-call engineer | As an on-call engineer, I want health checks, metrics, tracing, alerts, and runbooks so that failures are detected and recoverable. | Readiness checks dependencies; traces correlate request/job/provider/media/delivery IDs; SLO alerts cover latency/error/backlog; backup restore and provider outage runbooks are exercised. | P0 | Planned | Cloud staging | Operational readiness review | Metrics are specified; production telemetry and drills are missing.
VH-032 | M4 | E10 | FinOps | Product owner | As the product owner, I want usage quotas and cost alarms so that the initial cloud bill stays within the approved envelope. | Per-user/provider rate limits exist; daily spend estimate covers provider, queue, database, storage, and egress; alerts fire before budget exhaustion; abusive accounts can be throttled without affecting all users. | P0 | Planned | Provider pricing and Cloudflare production account | Cost model and load test | $5 target is an experiment assumption, not a production guarantee.
VH-033 | M5 | E11 | Language QA | Language reviewer | As a language reviewer, I want a scored evaluation set for all five languages so that launch voices and translations meet an explicit quality bar. | Native reviewers score intelligibility, pronunciation, naturalness, code-switching, and harmful mistranslation; provider/voice/version is recorded; minimum scores and rollback thresholds are approved. | P0 | Planned | Reviewer panel and provider candidates | Language quality sign-off | No production language evaluation report yet.
VH-034 | M5 | E11 | Android Release | Android user | As an Android user, I want a stable, accessible, signed application so that core flows work across supported devices. | Supported OS/device matrix passes create/play/share/auth/offline tests; crash-free threshold is met; TalkBack and large text are usable; Play signing, privacy labels, and store disclosures are complete. | P0 | Planned | M1-M4 gates | Play closed-test approval | Debug build passes locally; release configuration is incomplete.
VH-035 | M5 | E11 | Operations | Support agent | As a support agent, I want moderation, privacy, billing, delivery, and provider incident playbooks so that user reports receive consistent outcomes. | Runbooks define severity, owner, evidence access, response time, escalation, user communication, and closure; takedown and safety exercises complete before beta expansion. | P0 | Planned | Named operational owners | Launch operations drill | No complete production runbook set yet.
VH-036 | M5 | E12 | Analytics | Product manager | As a product manager, I want privacy-preserving product events so that I can measure whether people successfully create, listen, and return. | Events exclude message text/audio/phone numbers; funnel measures create start-to-share, channel follow-to-play, opt-in delivery, and companion return; consent and deletion rules apply to analytics identifiers. | P1 | Planned | Analytics provider and privacy review | Analytics schema review | Metrics are defined; instrumentation is not implemented.
VH-037 | M5 | E12 | Product | Beta owner | As the beta owner, I want staged cohorts and kill switches so that risky features can be expanded or stopped independently. | Create cloud voice, translation, WhatsApp delivery, and romantic companions have separate server-controlled flags; cohorts and rollback owner are documented; disabling a feature preserves user data and clear messaging. | P0 | Planned | Cloud configuration and telemetry | Controlled rollout test | No production feature-flag service is wired.
VH-038 | M5 | E12 | Product | Product team | As the product team, we want a weekly launch scorecard so that expansion decisions use agreed evidence rather than anecdotes. | Scorecard reports activation, successful shares, listening retention, provider error/latency, delivery opt-out, safety intervention, report rate, crash-free sessions, and cost per active user; owners review it weekly. | P1 | Planned | VH-031, VH-032, VH-036 | Beta governance cadence | Metric definitions exist in PRD baseline.

## Release Gates
VOICE HUB — RELEASE GATES
A milestone cannot graduate until its linked production evidence is complete
Gate ID | Gate | Criterion | Owner | Milestone | Status
G01 | Identity | Production OIDC/Firebase configuration is live and negative authorization tests pass. | Platform | M4 | Blocked
G02 | Voice and language quality | All launch language/provider combinations meet native-review thresholds with rollback versions recorded. | Language QA | M5 | Planned
G03 | Audio compatibility | Cloud and device paths produce valid playable Ogg/Opus across the supported Android and WhatsApp matrix. | Android + Backend | M1 | Planned
G04 | WhatsApp production | Verified Meta business/WABA, approved templates, signed public webhook, consent, opt-out, and delivery replay are verified. | Operations | M2 | Blocked
G05 | Editorial operations | Named owners, source/review records, jobs expiry/scam controls, advice boundaries, and takedown runbook are exercised. | Editorial Ops | M2 | Planned
G06 | Companion safety | AI disclosure, adult gating, semantic anti-manipulation evaluation, block/report, export/delete, and incident workflow pass review. | Trust & Safety | M3 | Blocked
G07 | Cloud operations | Staging load, queues, storage, observability, backups, rate limits, and cost alarms meet approved thresholds. | Platform | M4 | Planned
G08 | Android release | Closed testing, signing, store declarations, accessibility, supported-device coverage, and crash-free threshold are complete. | Android + QA | M5 | Planned

## References
VOICE HUB — WORKBOOK GUIDE & REFERENCES
How to maintain the plan and the authoritative technical references used
WORKBOOK RULES
1 | User Stories is the editable source of truth for status and priority.
2 | Roadmap and Epics progress are formula-derived from Done stories.
3 | Blocked means an explicit external dependency or unresolved production decision.
4 | Dates are intentionally absent until capacity and external approval owners commit them.
Reference | URL | Use | Reviewed
Spitch Speech API | https://docs.spitch.app/features/speech | Direct Ogg/Opus speech synthesis and Nigerian-language voices. | 2026-08-15
Spitch Translation API | https://docs.spitch.app/api/text/translate | Translation among English, Pidgin, Yorùbá, Hausa, and Igbo. | 2026-08-15
Android TextToSpeech | https://developer.android.com/reference/android/speech/tts/TextToSpeech | Installed-engine capability and local synthesis behavior. | 2026-08-15
Android TTS Engine | https://developer.android.com/reference/android/speech/tts/TextToSpeech.Engine | Language-data install and engine settings actions. | 2026-08-15
Android supported media formats | https://developer.android.com/media/platform/supported-formats | Opus platform support baseline. | 2026-08-15
AndroidX Media3 OggMuxer | https://developer.android.com/reference/androidx/media3/muxer/OggMuxer | Ogg container option for supported Android versions. | 2026-08-15
WhatsApp Cloud API audio message | https://www.postman.com/meta/whatsapp-business-platform/request/juzqcg2/send-audio-message-by-url | Server-originated audio delivery contract. | 2026-08-15
Cloudflare Workers pricing | https://developers.cloudflare.com/workers/platform/pricing/ | Cloud execution assumptions and limits. | 2026-08-15
Cloudflare D1 pricing | https://developers.cloudflare.com/d1/platform/pricing/ | Database cost and capacity assumptions. | 2026-08-15
Cloudflare R2 pricing | https://developers.cloudflare.com/r2/pricing/ | Audio object storage and egress assumptions. | 2026-08-15
Cloudflare Queues pricing | https://developers.cloudflare.com/queues/platform/pricing/ | Asynchronous synthesis and delivery cost assumptions. | 2026-08-15
Firebase pricing plans | https://firebase.google.com/docs/projects/billing/firebase-pricing-plans | Authentication billing assumptions. | 2026-08-15